FINRLX · THE UNIFIED RESEARCH DESK

SPEC-04

QA, Test Strategy & Risk Management Plan

Test Pyramid · Fixtures · Gates · Risk Register · RAID · Rollout

Specification Package “Operation One Desk” · Program LEAP Track B

Council-certified after 5 peer-review rounds (record: SPEC-00 §3)

v1.0 · 2026-07-07 · CONFIDENTIAL · Baseline: rotemyoeli/FINRLX @ cbea0fa

## Document control

Contents

| Field | Value |
| --- | --- |
| Document | SPEC-04 — QA, Test Strategy & Risk Management Plan |
| Owner / Author | Quality workstream; Security/Ops Reviewer and Quant Skeptic co-sign the gates |
| Reviewers | Full council; findings R3-Q1, R4-Q1, R4-Q2 applied (SPEC-00 §3) |
| Prime directive | Minimum-risk start of development: every MUST in SPEC-01/02/03 appears exactly once in the gate list below (R5-verified bijection) |

## Conventions used across the package

- Normative language (RFC-2119): MUST / MUST NOT / SHOULD / MAY carry their standard meanings; every MUST is testable and appears in the SPEC-04 gate list.

- Identifiers: Epics EP-x; user stories US-x.y; API contracts API-x; components CMP-x; tests are referenced by suite name; risks RSK-x; decisions DEC-x. Cross-document references use these IDs — the R5 consistency scan verified every reference resolves.

- Baseline: all “existing” claims refer to rotemyoeli/FINRLX @ main cbea0fa (backend 1,308/0; vitest 69/0). Anything not at that commit is marked NEW or CHANGED.

- Scope waves: W0 = truth verification (in progress); W1 = Desk core build; W2 = E7/E8 + sector + forums; W3 = living desk. Each requirement carries its wave.

- Question-Zero applies to specifications: a spec that defers a decision to the developer is defective. The R4 review verified the open-decisions register is empty; every DEC-x below is resolved, not pending.

# 1. Test strategy — the pyramid, mapped to this program

| Layer | Scope & tooling | What it proves |
| --- | --- | --- |
| Contract / unit (backend) | pytest on API-4 aggregator, API-6 method block, API-7 elevation fixtures (eligibility, tie-break, regime weight, all-ineligible), API-2 attach semantics, error envelope shapes; runs on 3.11 CI-parity | server truth: dial states, elevation logic, envelopes are exactly the SPEC-02 shapes |
| Invariant suites (existing, extended) | K1 one-price-truth + dash-wall doctrine extended to every Desk panel; wording scan over the copy module; synthetic-artifact repo scan; RL isolation regression | the zero-fiction and governance invariants survive the new surface |
| Component (frontend) | vitest + testing-library per CMP: exhaustive state switches (unknown enum = compile error), a11y roles/labels, drawer trap/restore, dial never-color-only | each component honors its SPEC-03 contract in isolation |
| Integration / e2e | Playwright: US acceptance rows verbatim (each Gherkin row = one spec), fault-isolation (kill one section, siblings live), deep-link restore, keyboard path | the assembled Desk behaves per PRD under real routing |
| Visual | Playwright screenshot script → the SPEC-03 §6 matrix (84 frames) + pixel-diff against approved baseline after first Design Authority sign-off | pixels, not markup — the lesson the program already paid for |
| Performance | Lighthouse CI budgets (NFR-1/3/5); API-4 handler timing assertion | budgets are gates, not aspirations |
| Accessibility | axe over the full state matrix | NFR-4 as a gate |

## 2. Fixture inventory (deterministic, no live providers in CI)

- FX-FULL: complete dossier, all six live — the golden path.

- FX-E7 / FX-E8: gated payloads with exact reason/detail_code values.

- FX-DIVERGE: lanes disagree beyond threshold.

- FX-THIN: ≤3 news items; partial XBRL periods.

- FX-NULLS: ≥3 null signals (collapse card); separate all-ineligible elevation case.

- FX-EMPTYCHAIN: pricechart data:null.

- FX-PARTIALJOB: timed_out with 3 completed stages.

- FX-STALE: freshness beyond policy → shimmer + revalidation.

- FX-INCIDENTS: 2 unseen S8 incidents incl. same-day duplicate (dedupe display check).

Fixtures are committed JSON, versioned with the API schemas; a schema-drift test fails if fixtures and Pydantic models diverge (R4-Q1).

## 3. Gate structure

### Per-merge gate (every PR)

- ruff + mypy + pytest -q (3.11) green; vitest + tsc + eslint (incl. raw-key and advice-verb rules) green; next build within budget.

- Invariant suites green; P3′ screenshots attached for touched states; Design Authority pixel review recorded in the PR.

- git ls-remote proof accompanies every remote-state claim (standing program rule).

### W1 exit gate (flag flip DESK_V2→ON)

| # | Gate item | Source |
| --- | --- | --- |
| G-1 | All EP-1…EP-5 acceptance rows green in e2e | SPEC-01 |
| G-2 | Full 84-frame matrix approved by Design Authority; baseline locked | SPEC-03 §6 |
| G-3 | axe clean over the matrix; keyboard path video attached | NFR-4 |
| G-4 | NFR-1/3/5 budgets green in Lighthouse CI on the production build | SPEC-01 §3 |
| G-5 | K-2/K-3 invariants green (zero-fiction; 100% drawer coverage) | Report §9.2 |
| G-6 | Ten-ticker production reality check: ≥90% signal population, zero dash-walls, dial-state distribution logged (K-4) — runs against production /ops/data-health, requires W0 complete | Report §9.2 |
| G-7 | Rollback rehearsal executed once (flag off → legacy desk in <1 min, no residue) | §5 below |

# 4. Risk register

Scored L×I on 1–5 scales; owner is a program role. Mitigations are commitments already encoded in the specs (referenced), not intentions.

| ID | Risk | L | I | Mitigation (binding ref) | Owner |
| --- | --- | --- | --- | --- | --- |
| RSK-1 | Production data layer under-populates signals (dash-wall class) and the Desk amplifies the emptiness | 3 | 5 | W0 completes before W1 flag-on; G-6 hard gate; K1 collapse card design makes residual gaps honest, not broken | Ops |
| RSK-2 | UI built blind again — visual quality fails operator review | 2 | 5 | P3′ merge law + 84-frame matrix + Design Authority pixel sign-off + browser-equipped environment mandated (G-2) | Design Authority |
| RSK-3 | Dial states diverge from panel reality (split-brain honesty) | 2 | 5 | Single source API-4; client inference banned (SPEC-02 tenet 3); exhaustive enum switch fails build on drift | Backend |
| RSK-4 | API-4 becomes the hottest endpoint / thundering herd | 3 | 3 | Fingerprint-cached recompute on write only; ETag/SWR; 20 rpm rate limit; p95 ≤50ms assertion (SO-1) | Backend |
| RSK-5 | Elevation rule read as prediction → credibility/regulatory exposure | 2 | 4 | Fixed ‘not a prediction’ caption; logic verbatim in drawer; wording scan; QS-2 protocol (fixtures) | Quant Skeptic |
| RSK-6 | Scope creep into engines during a feature freeze | 3 | 3 | Out-of-scope list in PRD §1; council classification ‘credibility exposure’; any engine diff on a Desk PR is an automatic FAIL | Orchestrator |
| RSK-7 | E7/E8 slip leaves the Desk looking permanently degraded | 3 | 2 | Gated states are designed product states (dashed grammar, honest copy) — the Desk is complete-by-design at 4/6 and 5/6; Blocked Reports track E-items | Operator |
| RSK-8 | Provider ToS / rate ceilings under Desk-driven refresh load | 2 | 4 | No per-view provider calls (dossier-cached); DAG budgets unchanged; data-health monitors per-source failure rates (NFR-8) | Ops |
| RSK-9 | State-matrix explosion makes reviews superficial | 2 | 3 | DEC-1 deferred compare; matrix capped at 14 named states; new states require a spec change, not just code | UX Critic |
| RSK-10 | Token/credential exposure (PAT re-exposed this program) | 3 | 4 | E1 rotation elevated to W1 precondition for CI-enforced gates; secrets never in fixtures; SECRETS_RUNBOOK applies | Operator + Security |
| RSK-11 | Drawer method content drifts from actual engine behavior over time | 2 | 4 | method blocks generated from the same constants the engines use where feasible; schema-drift test (R4-Q1); Truthfulness Auditor samples per release | Truthfulness Auditor |

## RAID summary

| Type | Items |
| --- | --- |
| Assumptions | Railway env vars manageable by operator in W0; Finnhub free tier stays sufficient for W1 fundamentals; recharts remains adequate (no new chart lib) |
| Issues (open now) | PAT exposed twice in operating channel (→ E1); production Finnhub key validity unverified (→ W0) |
| Dependencies | W1 flag-on ← G-6 ← W0; W2 scored social ← E8; W2 RL leg ← E7; CI gate enforcement ← E1 |
| Decisions | DEC-1…DEC-7 closed in SPEC-01; register empty (R4 verification) |

# 5. Rollout & rollback

- Build behind DESK_V2 (registry per D23), default OFF; legacy desk untouched and routable.

- Internal-on: flag ON for operator session only; operator runs the K-6 acceptance script on 3 tickers from the QA list.

- Flag-on requires G-1…G-7 green in one CI run; the flip commit carries the gate evidence links.

- Rollback = flag OFF: pure client-side route behavior, no data migration to unwind (by design — zero schema changes in W1); rehearsed once per G-7.

- Post-flip watch (72h): dial-state distribution, API-4 p95, section error rates by source, zero-fiction scan on schedule; regression on any → flag OFF + incident note, not hotfix-under-pressure.

Definition of Done — program level W1 is done when: the operator loads a QA-list ticker and sees the K-6 screen; every gate G-1…G-7 is green with committed evidence; the screenshot baseline is locked; and the deviations ledger contains zero unresolved rows. Nothing in this definition is subjective, which is the entire point.